## Instructions
Instructions for filling the Workplan Tracking Measures (WPTM)
WorkplanTracking Measures | Workplan Tracking Measures (WPTMs) are to be included for modules and interventions that do not have suitable coverage/output indicators to measure progress over the grant implementation period and/or when the module/intervention budget constitues ≥30% of the component budget, for example- CSS, Removing legal barriers to access, some interventions related to HSS, and interventions addressing gender inequalities, RMNCH linkages, Gender Based Violence, or any other disease specific interventions.
Intervention | Under each module, select the intervention related to the tracking measure from the drop down list. The interventions selected here should be linked to the interventions under detailed budget
Key Activities | 1. For each intervention include the activity to be monitored. 2. Criteria for selection of these activities could be: - Activities that constitute a high proportion of the grant budget - Activities that are considered high risk and require regular follow up - Activities that are critical in achieving the grant’s objectives 3. The selected activities should be linked to the activities in the module budget.
Milestones/Targets | 1. Identify the measures linked to the activities planned during the reporting period that will be used to track progress of their implementation. 2. These could include qualitative milestones and/or input/process measures with numeric targets (no more than 200 characters each) 3. 3-5 measures per reporting period could be included across various modules and interventions. The choice of these measures may vary from one period to another. All reporting periods need not have milestones/targets.
Criterion for completion milestone/target | Specify the criteion agreed between the country and the country team that will be used to assess the completion or achievement of a particular milestone/target. For example, for the milestone, "Needs assessment conducted", the criterion for completion could be that the report of the needs assessment is endorsed by relevant authorities and report publisehd and disseminated on the website.
Timelines | Indicate the period in which the milestone/target is due to be reported by selecting "X" from the drop down list.
Comments | Include any relevant information related to the selected activties and the WPTMs

## Concept Note-WPTM Annex
Concept Note- Workplan Tracking Measures
A. Program Details
Country/Applicant: |  | Bulgaria |  |  | Principle Recipients |  | Ministry of Health
Component |  | TB
Start year |  | 2015
Start month |  | October
B. Workplan Tracking Measures
Module: TB Care and Prevention
# | Intervention | Key Activities | Milestones/Targets (no more than 200 characters) | Criterion for completion milestone/target |  | Milestones/Targets | [7 empty] | Comments (no more than 500 characters)
[6 empty] | Period 1 | Oct 2015 - Dec 2015 | Jan 2016 - Jun 2016 | Jul 2016 - Dec 2016 | Jan 2017 - Jun 2017 | Jul 2017 - Dec 2017 | Jan 2018 - Jun 2018 | Jul 2018 - Sept 2018
1 | Other | Strengtheining the patient-centered approach to TB treatment | Feasibility study on the possible shift from hospital-based treatment to the ambulatory care designed - April 2015 | TOR prepared and sent to GF and WHO |  | x | [7 empty] | The finalization of the TOR and possible TA provision by the WHO is currently scheduled to complete during the extension period of the current grant (Round 8) before the start date of the NFM grant in October 2015.
|  |  | WHO mission in country for the feasibility study - May-June 2015 | Report received and dicussed withing MoH and with stakholders in a round-table |  | x
|  |  | Incorporation of the relevant feasible actions into the NSP - November 2015 | Approval of the NSP by the government |  |  | x
|  |  | Submission of the comprehensive strategy and detailed operational plan for the feasible shift - 31 March 2016 | MoH review and approval |  |  |  | x
2 | Other | Development of the Plan for transitioning away from the Global Fund Financing (Transition Plan) | Technical: Criteria of NGO contracting is updated | Mechanisms on selection, coordination, payment and M&E of the NGO activities to be developed and applied by MoH |  |  |  | x | [5 empty] | The general transition plan will be developed and included as an Annex to NSP by December 2015. A detailed plan will be submitted to the Global Fund Secretariat by 31 December 2016.
|  |  | Technical: Legal status of the TB medicines which can be procured through GDF determined. | Analysis of the legislation on drugs currently purchased under the GDF performed |  |  |  |  | x
|  |  | Organizational: Key posts for NGO work/oversight, reporting systems, including M&E assigned; and intergration of the NGO information system to the national system complete. | Plan with a justification of additional HR to be appointed at the Department approved; for supervising the work of the NGOs, M&E, and maintenance of TB registers and NGO information system | [5 empty] | x | x
|  |  | Financial: Ensuring budget allocation mechanisms for all activities currently funded under the GF, including HR and NGOs, under the NTP | Mechanisms ensuring that financial gaps are properly addressed are developed and incorporated in the NSP budget |  |  |  |  | x
3 | Treatment | Provision of treatment through DOTS at health facilities with quality assured anti-TB drugs procured with domestic funds for adult patients and for childhood TB cases. Fixed drug combinations will be procured from GDF with Global Fund financing. | Procurement of FDC for adults | FDC for 500 adults for 2 months procured |  |  |  | x |  | x |  |  |  | The guidelines will be finalized and submitted to the Global Fund Secretariat by December 2015. During the non-costed extension period, the PR will submit: - the updated diagnostic algorithm, including sample referral network and the geographic locations supported by justification for the four GeneXpert® machines. - the updated treatment guidelines, which specify the criteria under which the FDC will be applied.
|  |  | Updating the National Guidelines for terms and conditions for diagnostics, treatment, prophylaxis and infectious control. | National Guidelines on Diagnostics, Treatment, Prophylaxys and Infections Control updated |  |  | x
4 | Key affected populations (High risk groups) | Specific mobile screening activities will target KAP in the regions with the most poverty afflicted Roma population and refugees' centers. The mobile TB screening activities will be implemented in collaboration with TB health facilities and non-governmental organisations working with KAP. Motivation of patients to treatment adherence. | Specific algorythm for mobile screening activities in Roma population in 3 pilot areas and Refugees' centers developed; The algorithm will include guidance on time allocation amongst sub-recipients and risk groups throughout the year. | Algorythm for the use of the mobile fluorography unit and its integration into the routine screening activities developed. |  | x | x | [6 empty] | Screening algorithm would be shared with the Global Fund Secretariat. During the non-costed extension the PR will submit to the Global Fund Secretariat the algorithm for use of the mobile fluorography unit with description of how fluorography screening will be integrated into routine screening activities. For mobile digital fluorograph the PR should develop and share with the Global Fund the guidance on time allocation amonst sub-recipients and risk groups throughout the year.
|  |  | Tender documentation for the procurement of the mobile X-ray/fluorograph prepared | Tender started |  |  | x
|  |  | Mobile X-ray/fluorograph procured; organizational issues | Contracts signed |  |  |  | x
|  |  | Motivation of patients to adhere to therapy | Food vouchers contracted and provided to KAP |  | x | x | x | x | x | x | x | x
5 | Collaborative activities with other programs and sectors | Active case finding in prisons using mobile laboratory and fluorograph to be implemented by the NTP in collaboration with the Ministry of Justice and the Directorate of Prisons. | Development of an agreement with the MoJ on the active case finding in prisons and screening with fluorograph | Ordinance on joint activities in prisons signed |  |  | x
|  |  | Development of a specific timetable for the prisons to be visited, contracting services | Timetable developed and agreed with MoJ, permissions issued |  |  | x | x
|  |  | Data submitted; treatment started | Data analysis performed and recommendations issued |  |  |  |  | x |  | x
6 | Community TB care delivery | SR implementation Arrangements and SR Capacity Strengthening: 20 Roma NGOs selected and contracted to perform outreach activities in 20 Roma communities; 19 NGOs selected and contracted to perform outreach activities in KAP (refugees and migrants, chidlren at risk, homeless, IDUs); one NGO selected for organizing diabetics' screening for TB | NGO outreach to KAP plan development and selection of NGOs to perform activities among KAP | NGO outreach to KAP plan finalized; NGO/SR selection procedure finalized; funds disbursed |  |  | x | x | [5 empty] | NGO/SR capacity strengthening trainings would be included in the overall NFM grant training plan to be reviewed and approved by the Global Fund Secretariat
|  |  | Focused NGO/SR capacity strengthening trainings | Trainings conducted |  |  |  | x |  | x
|  |  | Procurement of consumables for outreach work | Tenders started and procurement contracts signed |  |  | x | x
|  |  | Review of SR implementation and update of the outreach plan | Plan updated | [5 empty] | x
7 | Engaging all care providers | Pilot treatment and follow-up of TB patients delivered by hired PHC specialists (in remote areas)/hospital specialists (in cities) will involve training of medical specialists on treatment and monitoring during the ambulatory phase | Algorythm for selection of TB specialists developed (PHC in remote areas; hospital specialists in cities) to provide ambulatory follow-up of TB patients | TB specialists selected and contracted |  |  | x | [6 empty] | Algorithm would be shared with the Secretariat prior to the roll out.
|  |  | Development of training modules for PHC specialists and district nurses organized in ambulatory follow-up of TB and MDR-TB patients | Trainings conducted |  |  |  | x |  | x
|  |  | Analysis of lessons learned; discussion with the MoH and health professionals | Analysis performed; round table conducted; recommendations issued | [6 empty] | x
|  |  | Updating the National Guidelines on treatment and follow-up of patients | As per the recommendations issued | [7 empty] | x
Module: MDR-TB
# | Intervention | Key Activities | Milestones/Targets (no more than 200 characters) | Criterion for completion milestone/target |  | Milestones/Targets | [7 empty] | Comments (no more than 500 characters)
[6 empty] | Period 1 | Oct 2015 - Dec 2015 | Jan 2016 - Jun 2016 | Jul 2016 - Dec 2016 | Jan 2017 - Jun 2017 | Jul 2017 - Dec 2017 | Jan 2018 - Jun 2018 | Jul 2018 - Sept 2018
1 | Case detection and diagnosis: MDR-TB | NTP will target the high risk groups using GeneXpert as the initial diagnostic test for all MDR-TB suspects, new smear positive, smear-negative and culture positive cases in some key populations during screening (TB symptomatics PLHIV, Xray positive prisoners, Xray positive Roma). | Revision of diagnostic algorithms, including sample referral network and the geographic location; Consultation with WHO and GF on the revised algorithm | Algo revised and agreed |  | x | x | [6 empty] | Finalized alogarithm is shared and submitted to the Global Fund Secretariat
|  |  | GeneXpert equipment for Real Time PCR for detection of M.tuberculosis and Rifampicin resistence and cartriges procured | GeneXpert machines procured |  |  | x
|  |  | Training of lab staff (online) | Training conducted |  |  |  | x
|  |  | Diagnostic algorithm implemented | Reports |  |  |  | x | x | x | x | x | x
2 | Treatment: MDR-TB | Ensuring quality treatment of all MDR-TB patients with SLD; prevention of drop-outs of treatment through provision of incentives for all MDR-TB patients to adhere to therapy | Procurement of second line drugs (SLD) for 50 patients from GDF. | Second-line anti-TB drugs for treatment of 50 MDR-TB patients procured and supplied (through GLC) |  |  |  | x |  | x |  |  |  | The quantification of SLD order is cleared by the Global Fund Secretariat prior to order submission to GDF.
|  |  | Provision of incentives for patients to avoid drop-outs | Food vouchers contracted and supplied to MDR-TB patients for adherence to treatment |  |  | x | x | x | x | x | x | x
3 | Engaging all care providers | Piloting the shift to ambulatory care through contracting of PHC speciliasts in remote areas to follow-up MDR_TB patients | PHC specialists (in remote areas)/hospital specialists (in cities) selected and contracted for ambulatory follow-up of MDR-TB patients | TB specialists selected and contracted |  |  | x | [6 empty] | National guidelines on MDR TB to be sumbitted to the Global Fund Secretariat
|  |  | Development of training modules for PHC specialists and district nurses organized in ambulatory follow-up of TB and MDR-TB patients | Trainings conducted |  |  |  | x |  | x
|  |  | Analysis of lessons learned; discussion with the MoH and health professionals | Analysis performed; round table conducted; recommendations issued | [6 empty] | x
|  |  | Update of the National guidelines on MDR-TB | As per the recommendations issued | [7 empty] | x
4
5
6
7
8
9
10
Module: TB-HIV
# | Intervention | Key Activities | Milestones/Targets (no more than 200 characters) | Criterion for completion milestone/target |  | Milestones/Targets | [7 empty] | Comments (no more than 500 characters)
[6 empty] | Period 1 | Oct 2015 - Dec 2015 | Jan 2016 - Jun 2016 | Jul 2016 - Dec 2016 | Jan 2017 - Jun 2017 | Jul 2017 - Dec 2017 | Jan 2018 - Jun 2018 | Jul 2018 - Sept 2018
1 | TB/HIV collaborative interventions | Improving access of all symptomatic PLHIV to GeneXpert and to strengthen the systematic symptom screening of PLHIV patients. | Development of national guidelines and operating procedures | Guidelines developed |  |  |  | x |  | x |  |  |  | The draft guidelines to be submitted to the Global Fund Secretariat and relevant technical partners.
|  |  | Training in TB/HIV collaboration for managerial staff in TB/HIV collaborative activities, including TB and HIV case detection, prevention, treatment and care | Training conducted | [5 empty] | x
2
3
4
5
6
7
8
9
10
Module: HSS - Health information systems and M&E
# | Intervention | Key Activities | Milestones/Targets (no more than 200 characters) | Criterion for completion milestone/target |  | Milestones/Targets | [7 empty] | Comments (no more than 500 characters)
[6 empty] | Period 1 | Oct 2015 - Dec 2015 | Jan 2016 - Jun 2016 | Jul 2016 - Dec 2016 | Jan 2017 - Jun 2017 | Jul 2017 - Dec 2017 | Jan 2018 - Jun 2018 | Jul 2018 - Sept 2018
1 | Routine reporting | Development and maintenance of the web-based HMIS on TB; Integration of the GF specific information systems into the National HMIS; | Building of a web-based information system with national coverage, real-time information on TB patients, their contacts and susects to be used by the Ministry of health; linkage between the TB health facilities, as well as a direct connection with NRL; direct observation of the patients’ status. | Linking of the Grant specific HMIS (TB register, NGO reporting system) with the National HMIS | [6 empty] | x |  |  | The plan for M&E system strengthening to be submitted to the Global Fund Secretariat for review and clearance.
|  |  | Creating a link between HIV and TB registers for easy follow up HIV-TB co-infected patient and their treatment outcome | Software of TB and HIV electronic information systems updated to link the two systems and maintained |  |  |  | x | x | x | x | x | x
|  |  | Finalization of the National M&E Plan (as part of the new NSP) | Plan finalized |  |  | x
|  |  | Strengthening of the M&E system (as per the developed Plan) | MESS completed |  |  | x | x | x | x
Module: Program management
# | Intervention | Key Activities | Milestones/Targets (no more than 200 characters) | Criterion for completion milestone/target |  | Milestones/Targets | [7 empty] | Comments (no more than 500 characters)
[6 empty] | Period 1 | Oct 2015 - Dec 2015 | Jan 2016 - Jun 2016 | Jul 2016 - Dec 2016 | Jan 2017 - Jun 2017 | Jul 2017 - Dec 2017 | Jan 2018 - Jun 2018 | Jul 2018 - Sept 2018
1 | Grant manamgement | Management and coordination of activities at national level, program administration, supervision and monitoring of SR activities; financial audit; developing of guidelines for health professionals for TB screening, referral and support | PMU staff contracted | Contracts signed |  |  | x |  | x |  | x |  |  | The draft guidelines to be submitted to the Global Fund Secretariat and relevant technical partners.
|  |  | Administration and overhead services contracted (running costs, communication, fuel etc) | Contracts signed |  |  | x
|  |  | On-site supervision and monitoring of activities at the local level | Reports developed |  |  |  | x | x | x | x | x | x
|  |  | Development of guidelines on TB screening, care and support | Guidelines developed

## Key questions-evaluation
Key Evaluation Questions
A. Program Details
Country/Applicant: |  |  | Principle Recipients
Component
Start year
Start month
B. Program Objectives
Objectives
1
2
3
C. Elements and Questions for Evaluation*
Objective 1.
# | Evaluation elements | Questions for Evaluation |  | Methods | Evaluator(s) | Timelines | Comments
1
2
3
4
5
Objective 2.
# | Evaluation elements | Questions for Evaluation |  | Methods | Evaluator(s) | Timelines | Comments
1
2
3
4
5
Objective 3.
# | Evaluation elements | Questions for Evaluation |  | Methods | Evaluator(s) | Timelines | Comments
1
2
3
4
5
*An operational evaluation protocol shall be developed, prior to the implementation of evaluation